## Requirements
High level requirement : | Employee onboarding process, develop a web application with the features of login with prodapt credentials.The HR professionals to get required approvals to onboard employeees and generate the link to the employee / candidate. The Employee to upload all the revelant documents in to the system. Transform the Image as digital data and extract to other applications across Prodapt. the application should also consider to have Microservices

## Design
Screen 1: Initiate Employee On Boarding Process | Initiate Employee On Boarding Process | [8 empty] | Screen 3: HR user (Admin) View employee OnBoarding Details
| HR Input Screen | [8 empty] | TL : In this Screen, Review comments, Review Date and Reviewed Button should be enabled only if the status is Submitted
| Name |  | Employee ID: |  | Screen 2: HR user (Admin) Dashboard |  |  |  |  | Employee ID | 700 | Search
| Offer letter date |  | Email |  | Employee ID | Employee Name | Status | Date of Onboarding | Action | Employee Name | Vaishnavi
| 1st level interviewer |  |  |  | 870 | Mahesh | InProgress | 2019-03-11 | View | Offer letter date
| 2nd level interviewer |  |  |  | 900 | Srijith | Pending | 2019-03-11 | View | Email
| Date of Joining |  |  |  | 901 | Vaishnavi | Submitted | 2019-03-11 | View | 1st level interviewer
| Date of OnBoarding Intiation | [8 empty] | 2nd level interviewer
| Status | Pending, InProgress, Submitted, Validated | [7 empty] | Date of Joining
[10 empty] | Status | Submitted
Welcome Srijith | Employee ID | Employee Name
Screen 1: Employee Onboarding File upload screen | Details Required | Uploaded by new Employee |  |  | Legends |  |  |  |  | Details Required | Uploaded by new Employee
| Educational |  |  |  | Text | HR Input Fields |  |  |  | Educational
| 10th Mark sheet |  | Comments: | Upload | Text | Employee Input Fields |  |  |  | 10th Mark sheet | image link will be displayed, Page1, … Page n.
| 12th Mark Sheet |  |  |  | Text | Read Only |  |  |  | 12th Mark Sheet
| UG Certificate | List down the courses |  | Upload |  | Employee Screen |  |  |  | UG Certificate
| PG Certificate | List down the courses |  | Upload |  | HR user (Admin) screen |  |  |  | PG Certificate
| any Degree or diploma | Free Text |  | Upload | [5 empty] | any Degree or diploma
| Technical Certificate | [8 empty] | Technical Certificate
| Technology |  |  | Upload | [5 empty] | Technology
| Professional | [8 empty] | Professional
Add (+) | Service letter from last company | Name of the company |  | Upload | [5 empty] | Service letter from last company
(-)
| Payslips | Month and Year Text |  | Upload | [5 empty] | Payslips
Add (+) | [7 empty] | (-)
| Address Proof |  |  | Upload | [5 empty] | Address Proof
| Passport Copy |  |  | Upload | [5 empty] | Passport Copy
| Pan Card |  |  | Upload | [5 empty] | Pan Card
| Aadhar Copy |  |  | Upload | [5 empty] | Aadhar Copy
| Offer Letter with Signature |  |  | Upload | [5 empty] | Offer Letter with Signature
| NDA |  |  | Upload | [5 empty] | NDA
Review comments
Submit
Reviewed Date
Reviewed

## Assumptions
1 | 1. Only Employee can access
2 | 2. Each services like professional, technical. It should be microservices. And deploy it in a docker.
3 | 3. Size of the documents
4 | 4. Decided to have documents types as Jpeg, PNG , PDF,

## Technology
Persistence |  | Mobile apps : | Employee OnBoardingPro, Employee Referral
Backend | MySQL |  | Tool name | Comments
Web Framework | Angular 6 with BootStrap | Framework | Ionic 3.9 - Hybrid | UI
Services | SpringBoot | Frontend | Angular - Cordova | UI
Docker | Kubernetes / Docker | Simulator | shows functionalities | kind of a tool, in the machine. A Testing tool to test the functionalities in the app. Kind of unit testing
Application server | Tomcat | emulator | gennymotion | is a tool used for mobile app testing. This will enable functionalities and UI.
CI/CD |  |  | Andriod SDK | will also have internal simulator
Visual studio code, Eclipse.
Studio Andriod SDK
|  | Database | MySQL. | Database.
|  | Cloud | any open source cloud | on hold.
|  | Microservices | Spring boot
|  | Docker | Kubernetes
|  | CI/CD | Jenkins

## Team
S.No | Emp # | Name | Load % | From Date | To Date
1 | 2838 | Banu B | 100 | 2019-03-04 | 2019-03-31
2 | 2967 | Vaishnavi S | 100 | 2019-03-04 | 2019-03-31
3 | 2962 | Srijith M | 50 | 2019-03-04 | 2019-03-31
4 |  | Mahesh Ku mar
5 |  | Lakshmi NarayananRaju
6 |  | Jagadessan
Karthick

## user stories
Banu B , Vaishnavi S, Srijith
Story ID | User stories | Task id | Activity | Start Date | End Date | Assigned | Target Date | Status | Updates
Suggest a Name for the tool (ProPad, QuickStep, Crawl-on)
S1 | Feasibility and technology | 101 | * How Mobile apps are deployed in Andriod | 2019-03-11 | 2019-03-13 | Banu |  | Completed
|  | 102 | * How Mobile apps are deployed in IoS, | 2019-03-11 | 2019-03-13 | Srijith |  | Completed | Prerequtics: MAC OS XCODE ID - Deployment. Only on MAC. Per user : $99 / Year Enterprise:$299 / Year With windows OS: can e create IOS.
|  | 103 | * How Mobile apps are deployed inWindows | 2019-03-11 | 2019-03-13 | Vaishnavi |  | Completed
|  | 104 | * Validate and review the Technology Stack from operational standpoint | 2019-03-11 | 2019-03-13 | Banu |  | Completed
|  | 105 | * One Consolidated Database connectivity for Mobile app irrespective to its OS. | 2019-03-11 | 2019-03-13 | Vaishnavi |  | Completed | No issues. MySQL will be used for any OS.
|  | 106 | * Areas of utilizing the microservices concepts like Email components, uploading images. | 2019-03-11 | 2019-03-13 | Jagadeesan,Mahesh |  | Completed | Each screen should be a individual services. Ex: initiate obBoarding, Validation,
|  | 107 | * Check Feasibility of Deploying the application with the existing unix server. Understand the deployment process of the mobile app. | 2019-03-11 | 2019-03-13 | Banu |  | Completed
|  | 108 | UX screens for Employee OnBoardingPro app - Wireframes |  |  | Karthick |  | In-Progress | Login wireframe is completed. Low and high fidelity- 2 days. Due date: 19/Mar/19. 21/Mar: Karthik is working on the Designing UI pages. Presented the screens and its navigation.
|  |  | UI screen prototype for Admin and Employee with First . APK fike |  | 2019-03-15 | All Team | 2019-03-15 | Completed | First .APK was released with just few screens
|  | 110 | Ionic 3.9.2, Docker, Andriod SDK, Kubernetes, Setup in local Environment. Install and configure MySQL should be in Unix server. |  |  | All Team |  | Completed | All the softwares installation needs to be completed by EOD today (15 Mar). Docker installation is pending. Server installation MySQL to be confirmed by Suriyakala. Jenkins and Docker installed.
|  | 111 | Overall Data model - Defining tables, ER relationship, Design |  |  | Mahesh, Banu | 2019-03-20 | Completed | 20:Mar-Completed ER diagram, Design and Data model. completed 98%
|  | 112 | Review the Data model |  |  | Mahesh | 2019-03-21 | Completed | 20:Mar-Data model reviewed, 21-Mar:need to review the ER diagram
|  | 113 | Setup the Jenkins in the server machine.. Build Try with the Deployment in docker |  |  | Suriyakala |  | In-Progress | Installed in local machine.. Refer talents and facing issues. Working on pipelines. Will try to complete atleast one- Target 21/3/19. Server deployments - Jenkins completed. Only Angular CI's Completed.
|  | 114 | Setup the Docker in the Server machine., Try with the mircoservices and deploy in Andriod SDK |  |  | Suriyakala |  | Pending | have to create ajob for configuring
|  | 113 | Development of Wireframes |  |  |  |  | In-Progress | Karthick:
|  |  | 1. HR Login (Admin) - Screens |  |  |  |  | In-Progress
|  |  | Initiation Screen : Initiate Employee On Boarding Process - UI, Service Layer, DB |  |  | Vaishnavi S | 2019-03-20 | Completed | 80%. Completed the Screen UI. UI validation part is in progress. Targetting on 21/3. Completed the UI validations and UI screen Development.
|  |  | Review UI Screen 1 |  |  | Vaishnavi S | 2019-03-20 | In-Progress | Need to bring in the UI which Karthick Designed.
|  |  | Setup all the softwares and configure in local machines |  |  | Srijith M | 2019-03-20 | Completed | Installations are done.. Able to connect springboot with MySQL. Inserted table and columns.
|  |  | Initiation Screen : Service Layer Design |  |  | Srijith M | 2019-03-21 | Completed | Banu working on uploading the documents into table. Srijith worked on creating the table and able to insert records into it. Need to figure out there is no unique tasks for srijith and banu.
|  |  | Initiation Screen : DB |  |  | Banu B | 2019-03-21 | Completed | Banu to comeup with DDL scripts for the tables and get it created in DB. DDL scripts are prepared and sent it for review
|  |  | Review DB DDL scripts |  |  | Mahesh | 2019-03-21 | Completed | Banu to share the scripts today. Reviewed the scripts and made changes to it and checked in SVN.
|  |  | Development of Dashboard - HR user screen - UI |  |  | Vaishnavi | 2019-03-22 | Completed
|  |  | Development of Dashboard - HR user screen - service layer |  |  | Srijith | 2019-03-22 | Completed
|  |  | Testing of Initiation Screen and Dashboard screen: |  |  | Team | 2019-03-22 | Completed
|  |  | .APK deployment for initiation and Dashboard screen |  |  | Team | 2019-03-22 | NA
|  |  | Internal Demo - 1.Enter the data in Initiate screen to initiate Employee onboarding process for a employee 2.the entered data should get retrieved in the Dashboard screen. No action is required, but it should show all the stored data. |  |  | Team | 2019-03-22 | Completed | Feedback: 1. All the services needs to be completed before 29th (Friday) 2. Incorporate the Karthick Screens in to app. Formatting.
|  |  | Screen 0: Login Page with UI and Service layer |  |  | Banu |  | Completed
|  |  | Screen 0: ldap integration with our app |  |  | Banu B | 2019-03-25 | Completed
|  |  | Welcome screen UI (Including Karthi UI recommendations) |  |  |  |  | Completed
|  |  | Login screen - Simple login screen which has input fields- username and password - UI |  |  | Vaishnavi |  | Completed
|  |  | Login screen -LDAP Service layer |  |  | Banu B |  | Completed
|  |  | Home screen 1 |  |  | Vaishnavi |  | In-Progress
|  |  | Home screen 2 |  |  | Vaishnavi |  | In-Progress
|  |  | Home screen 3 |  |  | Vaishnavi |  | In-Progress
|  |  | Employee profile - Landing page of Employee login - UI |  |  | Banu B |  | Completed
|  |  | Employee profile - Landing page of Employee login - Present LDAP Details |  |  | Banu B |  | Completed
|  | 113 | Demo to Lakshmi on UI flow for Employee OnBoardingPro 1. Wireframes from Karthi. 2. Wireframes and navigations from Team. |  |  | Team
|  | 114 | Demo to Lakshmi on UI flow for Employee referral app |  |  | Team
|  | 115 | Freeze the requirements and come up with Requirements understanding document or Scope document. This should include screen prototypes |  |  | Team
|  | 116 | Review the Requirements or scope of the project |  |  | Team
|  | 118 | Prepare SQL's for creating objects |  |  | Banu
User as Employee - 1st Flow
|  |  | Front End Development for OnBoardingPro |  |  | Vaishnavi
|  |  | Middleware Development for OnBoardingPro |  |  | Srijith, Banu
User as HR - 2nd Flow
|  |  | Front End Development for OnBoardingPro |  |  | Srijith
|  |  | Middleware Development for OnBoardingPro |  |  | Vaishnavi, Banu
Demo
Internal
Testing
SIT
System Integration Test cases preparations
Review TC's
ST deployment
System Test cases Execution
Review Test Results
Address and track defects for closure
UAT
Demo Deployment and release for Mangers
fix issues / suggestions
Demo Deployment and release for HR team
fix issues / suggestions
Prepare Release notes
Production Live
production environment setup
Implemenation and Go Live

## Screen Dev
S.No |  | SCREENS | DESCRIPTION | INITIAL UI | UPDATED UI (Karthick's Wireframe) | SERVICE | DATABASE
1 |  | Welcome screen | First screen of our app which contains the login button | Completed - Vaishnavi | Completed | NA | NA
2 |  | Login screen | Simple login screen which has input fields- username and password | Completed - Srijith | Completed | LDAP- completed (Banu) | Pending
3 |  | Home screen 1 | This screen contains the information of Prodapt | Completed- Vaishnavi | Completed | NA | NA
4 |  | Home screen 2 | This screen contains the information of Prodapt | Completed - Vaishnavi | Completed | NA | NA
5 |  | Home screen 3 | This screen contains the information of Prodapt | Completed - Vaishnavi | Completed | NA | NA
6 |  | Employee profile | Landing screen for the employee which shows the details from LDAP | Completed - Banu |  | LDAP- completed (Banu) | On-Hold
7 | Screen 1: Employee Onboarding File upload screen | Certificate upload | To upload employee's certificates | 4 sections documents UI .completed. Posting the document is pending. Targetting for today |  | Completed -Banu | NA
8 |  | Help | This contains the emergency contact information for the Employee | To be Reviewed .Mahesh |  | NA | NA
9 | Screen 1: Initiate Employee On Boarding Process | Initiate Employee on-boarding | To initiate new employee's details | Completed - Vaishnavi | Completed | Completed - Banu / Vaishnavi | Completed
10 | Screen 2: HR user (Admin) Dashboard | View list of employees / Dashboard | To view the list of employees along with their status | Completed - Vaishnavi | Completed | Completed | Completed
11 | Screen 3: HR user (Admin) View employee OnBoarding Details | View documents | To view the documents uploaded by each employee | 10% is t | Pending | Completed. | Pending
12 | Email Notifications | During HR submits the inititaion process |  | Pending |  | Pending | NA
13 | Email Notifications | During Employee submits the onboarding process |  | Pending |  | Pending | NA
14 | Deploy | Move to consolidated MySQL |  | Banu.. - Pending
Analysis on Mobile app - DB connectivity
Integration of View documents.
15 | Deploy | verify it in Mobile app using APK

## Data Model (hidden)
Table Name: | Column Name | Data type | Size | Null / Not null | Constraints | Comments | Valid Values
Propad_Initiate_employee | IE_ID | Number | 9 | Not Null | Primary Key | Primary key of the Table
Propad_Initiate_employee | IE_Date | Date | 10 | Not Null
Propad_Initiate_employee | IE_Emp_id | Number | 9 | Not Null | unique Key | Create unique index
Propad_Initiate_employee | IE_Emp_name | Varchar | 30 | Not Null
Propad_Initiate_employee | IE_Emp_email | Varchar | 50 | Not Null
Propad_Initiate_employee | IE_Emp_DOJ | Date | 10 | Not Null
Propad_Initiate_employee | IE_Int1 | Varchar | 30 | Not Null
Propad_Initiate_employee | IE_Int2 | Varchar | 30 | Not Null
Propad_Initiate_employee | IE_Status | Varchar | 12 | Not Null |  |  | Pending, InProgress, Submitted, Validated,Processed
Propad_Emp_EDU_Details | ED_ID | Number | 9 | Not Null | Primary Key
Propad_Emp_EDU_Details | ED_IE_ID | Number | 9 | Not Null | Foreign key
Propad_Emp_EDU_Details | ED_EMP_ID | Number | 9 | Not Null | Foreign key
Propad_Emp_EDU_Details | ED_EDU_SSLC | BLOB | 5MB | Not Null |  | Encrypt and save it in DB | Jpg, Png , Pdf
Propad_Emp_EDU_Details | ED_EDU_SSLC_Text | Varchar | 2000 |  |  | Encrypt and save it in DB
Propad_Emp_EDU_Details | ED_EDU_HSC | BLOB | 5MB | Null
Propad_Emp_EDU_Details | ED_EDU_HSC_Text | Varchar | 2000
Propad_Emp_EDU_Details | ED_EDU_DIP | BLOB | 5MB | Not Null
Propad_Emp_EDU_Details | ED_EDU_DIP_Text | Varchar | 2000
Propad_Emp_EDU_Details | ED_EDU_UG | BLOB | 5MB | Not Null
Propad_Emp_EDU_Details | ED_EDU_UG_Text | Varchar | 2000
Propad_Emp_EDU_Details | ED_EDU_PG | BLOB | 5MB | Null
Propad_Emp_EDU_Details | ED_EDU_PG_Text | Varchar | 2000
Propad_Emp_EDU_Details | ED_EDU_others | BLOB | 5MB | Null
Propad_Emp_EDU_Details | ED_EDU_others_Text | Varchar | 2000
Propad_Emp_EDU_Details | ED_EDU_Comments | Varchar | 100 | Null
Propad_Emp_Tech_Details | ET_ID | Number | 9 | Not Null | Primary Key
Propad_Emp_Tech_Details | ET_EMP_ID | Number | 9 | Not Null | Foreign key
Propad_Emp_Tech_Details | ET_TECH_Cert1 | BLOB | 5MB | Null
Propad_Emp_Tech_Details | ET_Tech_Cert1_Text | Varchar | 2000
Propad_Emp_Tech_Details | ET_TECH_Cert2 | BLOB | 5MB | Null
Propad_Emp_Tech_Details | ET_Tech_Cert2_Text | Varchar | 2000
Propad_Emp_Tech_Details | ET_TECH_Cert3 | BLOB | 5MB | Null
Propad_Emp_Tech_Details | ET_Tech_Cert3_Text | Varchar | 2000
Propad_Emp_Tech_Details | ET_TECH_Cert4 | BLOB | 5MB | Null
Propad_Emp_Tech_Details | ET_Tech_Cert4_Text | Varchar | 2000
Propad_Emp_Tech_Details | ET_TECH_Cert5 | BLOB | 5MB | Null
Propad_Emp_Tech_Details | ET_Tech_Cert5_Text | Varchar | 2000
Propad_Emp_Tech_Details | ET_TECH_comments | Varchar | 100 | Null
Propad_Emp_prof_details | EP_id | Number | 9 | Not Null | Primary Key
Propad_Emp_prof_details | Ep_Emp_id
Propad_Emp_prof_details | Ep_service_Cert1
Propad_Emp_prof_details | EP_Service_Cert1_text | Varchar | 2000
Propad_Emp_prof_details | Ep_service_Cert2
Propad_Emp_prof_details | EP_Service_Cert2_text | Varchar | 2000
Propad_Emp_prof_details | Ep_service_Cert3
Propad_Emp_prof_details | EP_Service_Cert3_text | Varchar | 2000
Propad_Emp_prof_details | EP_Payslip1
Propad_Emp_prof_details | Ep_Payslip1_text | Varchar | 2000
Propad_Emp_prof_details | Ep_payslip2
Propad_Emp_prof_details | Ep_payslip2_text | Varchar | 2000
Propad_Emp_prof_details | Ep_payslip3
Propad_Emp_prof_details | Ep_payslip3_text | Varchar | 2000
Propad_Emp_Per_Details | EPer_ID | Number | 9 | Not Null | Primary Key
Propad_Emp_Per_Details | EP_per_EMP_ID | Number | 9 | Not Null | Foreign key
Propad_Emp_Per_Details | EP_PER_ADDRESSProof | BLOB | 5MB | Not Null
Propad_Emp_Per_Details | EP_Per_Addressproof_Text | Varchar | 2000
Propad_Emp_Per_Details | EP_PER_PP | BLOB | 5MB | Not Null
Propad_Emp_Per_Details | Ep_per_pp_text | Varchar | 2000
Propad_Emp_Per_Details | EP_PER_PAN | BLOB | 5MB | Not Null
Propad_Emp_Per_Details | Ep_per_pan_text | Varchar | 2000
Propad_Emp_Per_Details | EP_PER_AADHAR | BLOB | 5MB | Not Null
Propad_Emp_Per_Details | Ep_per_aadhar_text | Varchar | 2000
Propad_Emp_Validation | EV_ID | Number | 9 | Not Null | Primary Key
Propad_Emp_Validation | EV_Emp_Id | Number | 9 | Not Null | Foreign key
Propad_Emp_Validation | EV_Review_dt | Date |  | Not Null
Propad_Emp_Validation | EV_Review_Comments | Varchar | 100
Propad_Audit_log | AL_ID | Number | 9 | Not Null | Primary Key
Propad_Audit_log | AL_IE_ID | Number | 9
Propad_Audit_log | AL_ED_ID | Number | 9
Propad_Audit_log | AL_ET_ID | Number | 9
Propad_Audit_log | AL_EP_id | Number | 9
Propad_Audit_log | AL_EPer_ID | Number | 9
Propad_Audit_log | AL_EV_ID | Number | 9
Propad_Audit_log | AL_TRANSACTION | Varchar | 50
Propad_Audit_log | AL_PAGE | Varchar | 50
Propad_Audit_log | AL_DATE | Date
Propad_Audit_log | AL_USERID | Varchar | 50 | Not Null
Propad_Audit_log | AL_EMP_ID | Number | 9 | Not Null
Propad_Audit_log | AL_COMMENTS | Varchar | 100
Propad_users | user_uid | Number | 9 | Not Null | Primary Key
Propad_users | user_userid | Varchar | 45
Propad_users | User_Email | Varchar | 50
Propad_users | user_empid | Varchar | 10
Propad_users | User_Dept | Varchar | 50
Propad_users | User_role | Varchar | 10